2013-01-14

A, 1

F, 1

D, 1

H, 3

B, 2

G, 7

C, 1

M, 2

L, 1

K, 2

J, 1

I, 1

E, 7

**Project – Simple Sales Centre**

**Pert Chart**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **TASK** | **Duration (days))** | **Prerequisite Tasks** |
| **A** | **Pert Chart** | **1** | **-** |
| **B** | **Market Research** | **2** | **A** |
| **C** | **UML Diagram** | **1** | **B** |
| **D** | **Proposal & Flow Chart** | **1** | **C** |
| **E** | **Programming – GUI components** | **7** | **D** |
| **F** | **Interim Audit** | **1** | **-** |
| **G** | **Programming – Main & Sub Classes** | **7** | **D** |
| **H** | **Programming – Combining the GUI components with the Main & Sub Classes** | **3** | **E,G** |
| **I** | **Debugging/Editing – GUI Components** | **1** | **H** |
| **J** | **Debugging/Editing – Classes Components** | **1** | **H** |
| **K** | **Beta Testing** | **2** | **I,J** |
| **L** | **Final Editing/Debugging** | **1** | **J** |
| **M** | **Presentation preparation** | **2** | **L** |
| **N** | **Submission – Presentation** | **1** | **M** |
|  |  |  |  |

\*The project will take 22 days when

the critical path is followed.

\*The company has 25 days to finish the project completely.

\*Critical path is drawn with red lines.

N, 1